## Sheet1
	1	2	3	4	5	6	7	8
	June	July	August	September	October	November	December	January
intial literature review
determine how to read from web
Project definition	hand in 22
gather full uers requirments
literature review
create simple prototype
use tool on online groups
user evaluation of tool
Check point				handin 28
use tool on MS group
enchance tool
evaluate tool
user evaluation of tool
write results and conclusions
Draft							handin 14
printing and checking of report
final report								handin 25